## WBS & Gantt Chart
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17
Real Estate CRM – 11-Week WBS & Gantt Chart
WBS ID | Task Name | Level | Deliverable | Duration | 1w | 2w | 3w | 4w | 5w | 6w | 7w | 8w | 9w | 10w | 11w
1.0 | Project Management & Coordination | 1 | Project Plan & Status Reports | 11w | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
1.1 | Project Setup & Workshops | 2 | Project Charter & Communication Plan | 1w | ■
1.2 | Team & Resource Management | 2 | Weekly Status Updates & Oversight | 11w | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
2.0 | Requirements & Business Analysis | 1 | Requirements & Process Specs | 2w | ■ | ■
2.1 | Initial Workshops & Workflows | 2 | Real Estate Workflow Specs | 1w | ■
2.2 | System Requirements Specification | 2 | System Specs & Backlog | 1w |  | ■
3.0 | System Architecture & Design | 1 | Design Documentation & ERD | 2w |  | ■ | ■
3.1 | Architecture & Database Design | 2 | ERD & PostgreSQL Schema Design | 1w |  | ■
3.2 | Process Modeling & UI/UX | 2 | BPM & Use Case Diagrams | 1w |  |  | ■
4.0 | System Development | 1 | Real Estate CRM System | 5w |  |  |  | ■ | ■ | ■ | ■ | ■
4.1 | Auth & Role Management Module | 2 | User Login & RBAC System | 1w |  |  |  | ■
4.2 | Property Inventory Management | 2 | Property Catalog & Filtering | 2w |  |  |  |  | ■ | ■
4.3 | Client & Deal Tracking Dashboard | 2 | Leads & Deal Pipelines Dashboard | 1w | [6 empty] | ■
4.4 | Viewing Schedule & Calendar | 2 | Integrated Viewing Calendar | 1w | [7 empty] | ■
4.5 | Analytics & Commission Reporting | 2 | Sales & Commission Reports | 1w | [7 empty] | ■
5.0 | Testing, Migration & Deployment | 1 | Deployed Working CRM | 3w | [8 empty] | ■ | ■ | ■
5.1 | Data Migration & Scripting | 2 | Migration Scripts & Initial Data | 1w | [8 empty] | ■
5.2 | System & Performance Testing | 2 | Test Results & Bug Fixes | 1w | [9 empty] | ■
5.3 | Cloud Deployment & Handover | 2 | Live Application & Documentation | 1w | [10 empty] | ■
Baxadir Nzamutdinov I24D ID:202490228

## Task Duration
Real Estate CRM – Task Duration & Schedule
WBS ID | Task Name | Duration | Start | End
1.0 | Project Management & Coordination | 11w | 1w | 11w
1.1 | Project Setup & Workshops | 1w | 1w | 1w
1.2 | Team & Resource Management | 11w | 1w | 11w
2.0 | Requirements & Business Analysis | 2w | 1w | 2w
2.1 | Initial Workshops & Workflows | 1w | 1w | 1w
2.2 | System Requirements Specification | 1w | 2w | 2w
3.0 | System Architecture & Design | 2w | 2w | 3w
3.1 | Architecture & Database Design | 1w | 2w | 2w
3.2 | Process Modeling & UI/UX | 1w | 3w | 3w
4.0 | System Development | 5w | 4w | 8w
4.1 | Auth & Role Management Module | 1w | 4w | 4w
4.2 | Property Inventory Management | 2w | 5w | 6w
4.3 | Client & Deal Tracking Dashboard | 1w | 7w | 7w
4.4 | Viewing Schedule & Calendar | 1w | 8w | 8w
4.5 | Analytics & Commission Reporting | 1w | 8w | 8w
5.0 | Testing, Migration & Deployment | 3w | 9w | 11w
5.1 | Data Migration & Scripting | 1w | 9w | 9w
5.2 | System & Performance Testing | 1w | 10w | 10w
5.3 | Cloud Deployment & Handover | 1w | 11w | 11w

## Project Summary & Budget
Real Estate Property & Client Management CRM - Summary
Project Overview
Project Name | Real Estate Property & Client Management CRM
Customer | Prime Estate Agency LLC (Michael Scott, Managing Director)
Development Team | DevCraft Studio (Alex Smith, Lead Software Architect)
Agreement Date | September 15, 2026
Project Timeline | October 1, 2026 – December 15, 2026 (11 Weeks)
Total Budget | $14,000 USD
Payment Milestone | Percentage | Amount (USD) | Trigger / Condition
Initial Deposit | 40% | 5600 | Upon signing agreement
Intermediate Milestone | 30% | 4200 | After core backend & property inventory module delivery
Final Acceptance | 30% | 4200 | Upon final acceptance and handover
Total | 100% | 14000